## Sheet1
ID | Module / Area | Bug / Issue | Impact / Observation | Status
BUG-01 | UART TX FSM | Invalid/unsupported 2'b11 state handling | TX FSM had incorrect handling of the 2'b11 configuration/state condition, requiring correction of the state logic. | Fixed
BUG-02 | UART RX FSM | Invalid/unsupported 2'b11 state handling | RX FSM had incorrect handling of the 2'b11 condition, requiring RTL correction. | Fixed
BUG-03 | Baud Generator | Incorrect/incomplete baud generation | Baud-generation logic was not producing the required timing correctly and required major RTL correction. | Fixed
BUG-04 | Baud Generator / UART RX-TX | Missing baud16_tick generation/use | UART RX/TX sampling/transmission depended on a 16× baud tick that was missing/not correctly integrated. | Fixed
BUG-05 | UART FSM | UART FSM implementation/structure issue | UART FSM logic was not correctly implemented for the intended UART operation and required substantial RTL modification. | Fixed
BUG-06 | FIFO | FIFO depth/configuration issue | FIFO implementation/configuration had an incorrect depth relationship that caused simulation issues; FIFO depth was corrected. | Fixed
BUG-07 | TX Interrupt | TX interrupt clear through UARTICR did not clear the corresponding interrupt/status | TXRIS/TXMIS remained asserted after the clear operation. | RTL Issue
BUG-08 | RX Interrupt | RX interrupt clear through UARTICR did not clear the corresponding interrupt/status | RXRIS/RXMIS remained asserted after the clear operation. | RTL Issue
BUG-09 | Parity Error Interrupt | Parity-error interrupt/status was not correctly exposed/cleared | Parity-error status/interrupt corresponding to the parity-error bit was not asserted/cleared as expected during verification. | RTL Issue
BUG-10 | Framing Error | Framing error detected internally but not propagated to interrupt/status | o_RX_Errs[0] was observed asserting in the waveform, but UARTRIS[7]/UARTMIS[7] were not asserted as expected. | RTL Issue
BUG-11 | Overrun Error | Overrun error/interrupt not correctly exposed | Overrun condition was exercised by the UVM test, but the expected externally visible error/interrupt behavior was not achieved. | RTL Issue